## About
SpecWindow State Project Scan: Indiana
Public government records about data center projects dated Apr 18, 2026 to Oct 18, 2026. Issued Oct 20, 2026.
Projects with an opened government record: 7. Leads listed separately (reported in news or by trackers, on pages we could not open, or outside scope): 7.
Every project row links to the government record it rests on. Equipment, milestones and risks appear only where a linked source states them.
News comparison: whether we found a news story dated before, on, or after the record date. It is not a claim that the project was unknown.
Coverage is limited to the sources listed on the Sources tab. Some government sites block automated reading; see Coverage gaps. This is not a complete list of every project in the state.
No build probability or purchase prediction is given. Stages and risks are as stated in public records on the date checked.
Priorities tab: each project is marked Investigate now, Monitor or Deprioritize by fixed rules stated on that tab. Planned equipment in a permit is not a purchasing opportunity; procurement evidence is shown only where a source states it.
Stage, next step and procurement were checked on Oct 20, 2026.
SpecWindow, hello@specwindow.com, specwindow.com

## Priorities
Priority | Why | Buying window | Equipment points | Scale point | Timing test | ID | Project | County | Stage as of check | Stage detail | Stage source | Equipment categories stated | Equipment stated | Next verified step date | Next verified step | Next step source | Last decision date | Last decision | Last decision source | Organizations named in sources | Organization sources | People named in public records | Procurement evidence | Procurement source | Scale as stated | Legal challenge | Important unknowns | Suggested next research step
Investigate now | New equipment quantified in a government record; next public step Nov 17, 2026; buying window: open or upcoming (permitting or approval stage with no report of equipment secured) | Open or upcoming | 2 | 0 | Pass | IN005 | Lavender Fields Holdings data center expansion, 402 Royal Road (Google Michigan City) | LaPorte | Permit pending | The IDEM draft modification adding 66 critical generators to the permitted Lavender Fields data center is under public comment through Nov 23, 2026, with a virtual hearing on Nov 17, 2026. | https://permits.air.idem.in.gov/50515d.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions | backup generators; fuel storage; cooling | Draft modification: 66 new diesel critical emergency generators GEN67 to GEN132 at 3,490 kWe (4,680 bhp) each, plus one ancillary generator HUB1 at 167.6 bhp and 67 belly tanks; HUB1 may account for the notice's count of 67 critical generators, but no document says so; 66 existing generators at 2,750 kWe; 2 existing generators and belly tanks removed; HVO secondary fuel; closed loop air cooling system. | Nov 17, 2026 | IDEM virtual public hearing on the draft modification; the extended comment period ends Nov 23, 2026 | https://permits.air.idem.in.gov/50515d.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions | Mar 19, 2026 | IDEM approval of the initial data center air permit announced, reported by ABC57 | https://abc57.com/news/idem-approves-air-permit-request-for-michigan-city-data-center | Lavender Fields Holdings, LLC (applicant and permittee); Google (reported owner of the site, reported by news); Phoenix Investors (site owner since 2022 before the Google acquisition, reported by news); Michigan City Economic Development Corporation (awarded the project tax exemptions in July 2025, reported by DCD); Indiana Department of Environmental Management (permit decision body) | https://permits.air.idem.in.gov/50515d.pdf https://www.datacenterdynamics.com/en/news/google-takes-over-project-maize-data-center-campus-in-michigan-city-indiana/ https://nwindianabusiness.com/ov82 | Bailee Hyslope, applicant contact addressed in the IDEM cover letter, draft modification package; Omar El Rjoob, IDEM Office of Air Quality permit contact, draft modification package | None found |  | About 832 million dollars, one existing vacant building on a 70 acre former brownfield at 402 Royal Road, more than 500 construction workers needed (Northwest Indiana Business, Apr 17, 2026; DCD Apr 20, 2026); no MW stated. | no | General and electrical contractors; construction schedule; which utility supply arrangement serves the site | Attend or read the record of the Nov 17, 2026 IDEM virtual hearing, and check the Michigan City building department for permits at 402 Royal Road.
Investigate now | New equipment quantified in a government record; large stated scale (About $7 billion (DCD; Northwest Indiana Business)); next public step Nov 10, 2026; buying window: open or upcoming (permitting or approval stage with no report of equipment secured) | Open or upcoming | 2 | 1 | Pass | IN003 | Amazon Data Services data center campus, 2938-2778 County Rd 1350 N, Wheatfield | Jasper | Permit pending | The IDEM draft Part 70 air permit for the new Amazon data center is under public comment through Nov 16, 2026, with a virtual hearing on Nov 10, 2026. | https://permits.air.idem.in.gov/50413d.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions | backup generators; fuel storage | Draft permit Section A: 384 diesel critical emergency generators CEG1 to CEG384 at 2,750 kWe (4,043 bhp) each with SCR and cDPF (Section D.1 describes the same 384 but numbers their control systems CE1 to CE234, and its CO equation cites CEG1 to CEG234); 1 ancillary generator at 1,600 kWe; 4 house generators HG1 to HG4 at 750 kWe; 384 belly tanks of 6,500 gallons and 14 bulk tanks of 12,000 gallons. | Nov 10, 2026 | IDEM virtual public hearing on the draft permit; the extended comment period ends Nov 16, 2026 | https://permits.air.idem.in.gov/50413d.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions |  | County officials approved the Project Rise data center, reported by Northwest Indiana Business Magazine as Jun 17, 2026; the County Council agenda for Jun 16, 2026 lists Amazon abatement and exemption agreement resolutions, but no county record of their outcome was found, so the decision date is not confirmed | https://nwindianabusiness.com/ql0r https://www.jaspercountyin.gov/meetings/meeting-documents/county-council/2026-county-council-meetings/2026-county-council-meetings-agendas/622-06-16-2026-county-council-agenda/file | Amazon Data Services, Inc. (applicant); NIPSCO (site landowner, reported by news; also an abatement applicant on the same County Council agenda); Jasper County Council (abatement decision body); Indiana Department of Environmental Management (air permit decision body); Northwest Indiana Forum (worked with Amazon, reported by news); Shirley Heinze Land Trust (habitat restoration partner, reported by news) | https://permits.air.idem.in.gov/50413d.pdf https://www.jaspercountyin.gov/meetings/meeting-documents/county-council/2026-county-council-meetings/2026-county-council-meetings-agendas/622-06-16-2026-county-council-agenda/file https://nwindianabusiness.com/ql0r https://www.datacenterdynamics.com/en/news/amazon-plans-nine-building-data-center-campus-in-wheatfield-indiana/ | Phillip Jackson, IDEM Office of Air Quality permit contact, Amazon Wheatfield draft permit | None found |  | Up to nine buildings on a 304 acre NIPSCO owned site, about 7 billion dollars (DCD Jun 3, 2026 and Northwest Indiana Business Jun 18, 2026); County Council agenda May 19, 2026 lists a 330 acre Economic Revitalization Area; no MW stated for the site. | no | General and electrical contractors; construction start date; which utility facilities will serve the campus and whether they are the GenCo plants at Schahfer | Attend or read the record of the Nov 10, 2026 IDEM virtual hearing and comment file, and check the Jasper County plan commission and building department for a site plan.
Monitor | Equipment quantified but unclear whether it is new; large stated scale (An $11 billion New Carlisle investment (AP, Apr 25, 2024)); next public step Nov 18, 2026; buying window: unclear (sources do not show whether the equipment is new or already installed) | Unclear | 1 | 1 | Pass | IN004 | Amazon Data Services New Carlisle campus generator modification, 31100 State Road Highway 2 | St. Joseph | Operating site, expansion | The IDEM modification adding two 1,600 kWe generators to the operating New Carlisle campus had no final permit found as of Oct 20, 2026, and IDEM posted a further draft modification for a new generator building on Oct 19, 2026. | https://permits.air.idem.in.gov/50312d.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions | backup generators; fuel storage; buildings and shell | Draft modification: two ancillary emergency generators AWB1 and AWB2 at 1,600 kWe each, approved in 2026 for construction; the permit also lists 234 critical emergency generators at 2,750 kWe (4,043 bhp) constructed in 2025 and 2026, 9 house generators at 750 kWe, and ancillary units at 400 and 250 kWe. Separate draft posted Oct 19, 2026: a new building with one new diesel emergency generator and diesel tanks, rating not stated. | Nov 18, 2026 | End of the public comment period on the new IDEM draft modification for a new generator building at the same campus | https://www.in.gov/idem/public-notices/public-notices-all-regions https://www.in.gov/idem/files/notice_20261118_air_50362-50375pn-js.pdf | May 1, 2025 | IDEM issued the campus Part 70 operating permit (the most recent issued decision printed in the records opened) | https://www.in.gov/idem/files/notice_20260916_air_50312pn-as.pdf | Amazon Data Services, Inc (applicant and operator); Indiana Department of Environmental Management, Office of Air Quality (permit decision body) | https://www.in.gov/idem/files/notice_20260916_air_50312pn-as.pdf https://permits.air.idem.in.gov/50312d.pdf | David Monaghan, Amazon Data Services, Inc., addressee of the IDEM cover letter, draft modification; Emily Skelton, IDEM Office of Air Quality permit reviewer and comment contact for this modification, cover letter and notice; Alexandrea Neuzerling, IDEM permit reviewer named in the permit page headers and contact on the Oct 19, 2026 notice | None found. WVPE reports IDEM found two 1,600 kW generators already installed under a 1,500 kW permit (letter dated Jun 8, 2026), so the two units in this modification may already be on site; this is installed equipment, not a purchasing opportunity. | https://www.wvpe.org/wvpe-news/2026-06-16/amazon-data-center-violates-air-permits-in-multiple-ways | Amazon says it applied for permits for 911 generators across the two New Carlisle campuses (reported by ABC57, Jul 10, 2026). | no | Whether the two 1,600 kWe units in this record are the ones already installed; the rating of the generator in the new building; contractors on the campus | Read the Oct 19, 2026 IDEM draft modification package for the new building generator rating before the Nov 18, 2026 comment deadline, and check the IDEM permit site for a final decision on this modification.
Monitor | New equipment quantified in a government record; large stated scale (More than $10 billion and about 1 GW for the Meta Lebanon campus (IEDC; ACS Group)); decision Sep 25, 2026; buying window: early packages may be bought (construction is reported under way; later phases unknown); a source names a contractor | Early packages may be bought | 2 | 1 | Pass | IN001 | Orla LLC data center, 3062 West SR 32, Lebanon | Boone | Under construction | Meta broke ground on its Lebanon LEAP campus on Feb 11, 2026 (reported by IEDC and in an ACS Group press release), and IDEM issued the final permits for the Orla, LLC data center and the companion Life Cycle Power gas engine plant on Sep 25, 2026; the tie between Orla and Meta rests on IBJ reporting, as neither the IEDC release nor the permits name the other. | https://iedc.in.gov/events/news/details/2026/02/11/gov.-braun-breaks-ground-on-10b-meta-data-center-campus-at-leap-district https://pressroom.grupoacs.com/en/news/turner-selected-as-one-of-the-contractors-for-meta-data-center-campus-in-indiana https://permits.air.idem.in.gov/50034f.pdf https://www.ibj.com/articles/lebanon-commission-to-review-metas-15-building-data-center-project | backup generators; fuel storage; on site power generation | Orla permit: 12 diesel emergency generators EG1 to EG12 at 4,376 bhp each (draft offered a Caterpillar or a Cummins option; the final permit names no make), HVO as secondary fuel; 2 diesel fire pumps at 224 bhp; 12 belly tanks of 7,185 gallons. Life Cycle Power permit, treated by IDEM as one source with Orla: 65 natural gas Caterpillar G3516H engine generators GEN1 to GEN65 at 2,763 hp each with SCR and oxidation catalysts, and 2 regasification boilers at 5.4 MMBtu/hr. |  |  |  | Sep 25, 2026 | IDEM final permit for Orla, LLC (approval, effective immediately); IDEM issued the Life Cycle Power permit the same day | https://permits.air.idem.in.gov/50034f.pdf | Orla, LLC (applicant and permittee); Meta (reported parent of Orla, LLC, reported by news); Life Cycle Power (permittee of the on site power generating facility treated as one source with the data center); Indiana Department of Environmental Management, Office of Air Quality (permit decision body); Turner Construction Company (one of several contractors selected by Meta for its Lebanon campus, reported by ACS Group press release); Indiana Economic Development Corporation (state incentive for the Meta LEAP campus) | https://permits.air.idem.in.gov/50034f.pdf https://permits.air.idem.in.gov/50087f.pdf https://www.ibj.com/articles/lebanon-commission-to-review-metas-15-building-data-center-project https://pressroom.grupoacs.com/en/news/turner-selected-as-one-of-the-contractors-for-meta-data-center-campus-in-indiana https://iedc.in.gov/events/news/details/2026/02/11/gov.-braun-breaks-ground-on-10b-meta-data-center-campus-at-leap-district | Phillip Jackson, IDEM Office of Air Quality permit reviewer and comment contact, Orla and Life Cycle Power permits | Turner Construction Company was selected by Meta as one of the contractors for the Lebanon campus (per an ACS Group press release dated Feb 13, 2026); the link to this permit rests on IBJ reporting that Orla, LLC is a Meta subsidiary. No generator or engine order found; the Caterpillar models named in the permits are permitted equipment, not evidence of a purchase. | https://pressroom.grupoacs.com/en/news/turner-selected-as-one-of-the-contractors-for-meta-data-center-campus-in-indiana https://www.ibj.com/articles/lebanon-commission-to-review-metas-15-building-data-center-project | Meta campus: more than 10 billion dollars over up to six phases, about 1,500 acres, 13 buildings including 10 data center buildings (IEDC, Feb 11, 2026); about 1 GW and about 4 million square feet (ACS Group press release). The permits give no MW for the site. | no | Who holds the electrical and mechanical packages besides Turner; whether the 65 gas engines and 12 diesel generators have been ordered; the Life Cycle Power plant MW output and fuel delivery arrangement | Watch for any petition for administrative review of the Sep 25, 2026 permits at the Office of Administrative Law Proceedings, and check the Lebanon and Boone County building permit records for the Orla and Life Cycle Power site plans.
Monitor | New equipment quantified in a government record; large stated scale (2,600 MW combined cycle plus 400 MW battery (IURC order 46362)); next public step Jan 1, 2027; buying window: main equipment may be bought (a source reports equipment or construction contracts secured) | Main equipment may be bought | 2 | 1 | Pass | IN007 | NIPSCO special contract and GenCo supply for Amazon data centers in northern Indiana | Statewide or unnamed | Utility power supply approved or pending | The IURC approved the NIPSCO and GenCo special contract and power purchase agreement for Amazon in an order dated Jun 17, 2026, and in Cause 46362 the IURC declined to exercise jurisdiction over the GenCo plants, finding them reasonable and necessary only for the limited purpose of settlement compliance; second, third and fourth amendments to the Amazon special contract (Cause 46442) were heard on Oct 5, 2026. | https://www.in.gov/iurc/files/ord_46322_061726.pdf https://www.in.gov/iurc/files/ord_46362_061726.pdf https://www.in.gov/iurc/files/Hearings%20List%20for%20wk%20of%20October%205,%202026.pdf | utility power plants; UPS or batteries | IURC order 46362: two 1,300 MW combined cycle gas plants at the Schahfer Generating Station in Jasper County, built by converting two pairs of combustion turbines (2,600 MW), and a 400 MW battery storage system at the former Mitchell Generating Station in Lake County; up to 3,000 MW in total. These are utility plants, not on a data center site. | Jan 1, 2027 | Planned start of energization of Amazon load under the special contract | https://www.in.gov/iurc/files/ord_46322_061726.pdf https://www.in.gov/iurc/files/ord_46362_061726.pdf | Jun 17, 2026 | IURC orders in Cause 46322 (special contract, power purchase agreement and settlement) and Cause 46362 (the Commission declined to exercise jurisdiction over the GenCo generation resources; not a preapproval of cost recovery) | https://www.in.gov/iurc/files/ord_46322_061726.pdf https://www.in.gov/iurc/files/ord_46362_061726.pdf https://scanx.trade/stock-market-news/companies/nisource-secures-approval-for-amazon-data-center-deal/43764481 | Northern Indiana Public Service Company LLC (utility, joint petitioner); NIPSCO Generation LLC, now NiSource Generation Company LLC (generation owner and builder); Amazon Data Services, Inc. (customer); Indiana Utility Regulatory Commission (decision body); Office of Utility Consumer Counselor (party); Citizens Action Coalition of Indiana (intervenor, opposed the settlement); NIPSCO Industrial Group (intervenor); Board of County Commissioners of LaPorte County (intervenor); Blackstone Investor (minority investor in the GenCo parent, per NiSource filing) | https://www.in.gov/iurc/files/ord_46322_061726.pdf https://www.in.gov/iurc/files/ord_46362_061726.pdf https://www.sec.gov/Archives/edgar/data/0001111711/000111171126000088/nix-20260630.htm | Daniel L. Douglas, President and Chief Operating Officer, NIPSCO Generation LLC, named for the petitioner in IURC order 46362 | In testimony summarized in IURC order 46362, GenCo President Daniel L. Douglas stated that GenCo has entered into contracts with engineering, procurement and construction contractors and has secured the necessary equipment for the battery and gas plants, including turbines, and that GenCo expected to begin construction in the second quarter of 2026. This is company testimony, not a Commission finding, and no contractor or vendor is named. | https://www.in.gov/iurc/files/ord_46362_061726.pdf | Amazon load ramps to 2,400 MW by the end of 2032; about 7 billion dollars of generation and transmission investment per NIPSCO testimony as summarized in order 46322; NiSource reported an additional 400 MW for Amazon on its May 6, 2026 earnings call. | no | Names of the EPC contractors and the turbine supplier; balance of plant and substation packages still open; what the Cause 46442 amendments add and when they are decided | Watch IURC Cause 46442 for the order on the Amazon contract amendments and IURC Cause 46362 for compliance filings that may name contractors.
Monitor | Equipment named but not quantified in a government record; large stated scale (Initial investment of $2 billion (IURC order)); no dated public step within 120 days; buying window: unclear (sources do not show whether the equipment is new or already installed); legal challenge pending | Unclear | 1 | 1 | No | IN006 | Google Fort Wayne data center (Hatchworks LLC), 7510 Zodiac Way | Allen | Operating site, expansion | The campus is operating: IDEM reissued the permit for 140 added generators on Jun 1, 2026 and residents petitioned EPA on Jul 24, 2026 to object, with no EPA response found; for a Phase 3 expansion with three more buildings, IDEM issued water quality certification WQC001454 on Jun 5, 2026, and isolated wetland permit SRIP01408, heard Aug 25, 2026, has no decision found. | https://www.epa.gov/system/files/documents/2026-08/hatchworks-petition_7-24-26.pdf https://www.hecweb.org/wp-content/uploads/2026/06/WQC001454-Section-401-WQC-Approval.pdf https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf | backup generators; fuel storage; cooling; buildings and shell | Per the residents' petition to EPA, not a government record: 174 diesel emergency generators at 4,043 bhp each, about 525 MW combined (34 approved in 2024, 140 approved in 2025 for construction), 179 diesel tanks of 6,000 gallons, 64 cooling towers at 6,000 gpm. The 2024 IDEM permit, the only IDEM permit opened, lists 34 generators. Phase 3, per the IDEM water quality certification and wetland notice: three additional buildings, utility infrastructure, internal drives and stormwater facilities. |  |  |  | Jun 5, 2026 | IDEM Office of Water Quality issued Section 401 water quality certification WQC001454 for Project Zodiac Phase 3 (three more buildings); the copy read was posted by the Hoosier Environmental Council | https://www.hecweb.org/wp-content/uploads/2026/06/WQC001454-Section-401-WQC-Approval.pdf https://www.hecweb.org/2026/06/19/despite-opposition-idem-issues-water-quality-certificate-for-project-zodiac-data-center/ | Hatchworks, LLC (air permittee); Google LLC through a special purpose entity (customer in the IURC order); Indiana Michigan Power Company (utility); American Electric Power (parent of the utility); Indiana Utility Regulatory Commission (decision body); Indiana Department of Environmental Management (air permit body); Citizens Action Coalition of Indiana (intervenor); Barnes and Thornburg LLP (applicant counsel, per the petition); Fort Wayne City Utilities (water supplier, per the petition); EMH&T (agent for the applicant on the Phase 3 water quality and wetland filings); IDEM Office of Water Quality (water quality certification and wetland permit body); Hoosier Environmental Council (opposed the certification, reported by HEC) | https://secure.in.gov/iurc/files/ord_46276_042926.pdf https://www.epa.gov/system/files/documents/2026-08/hatchworks-petition_7-24-26.pdf https://permits.air.idem.in.gov/47378f.pdf https://www.hecweb.org/wp-content/uploads/2026/06/WQC001454-Section-401-WQC-Approval.pdf https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf https://www.hecweb.org/2026/06/19/despite-opposition-idem-issues-water-quality-certificate-for-project-zodiac-data-center/ | Aaron McGarry, Hatchworks LLC, applicant named on the IDEM isolated wetland permit notice; Marc Stern, Hatchworks LLC, addressee of IDEM water quality certification WQC001454; Heather Dardinger, EMH&T, agent named on the wetland notice and the water quality certification; Emersyn Harriman, IDEM Office of Water Quality project manager, water quality certification WQC001454; Omar El Rjoob, IDEM permit reviewer, Hatchworks air permit | None found |  | Initial investment 2 billion dollars announced April 2024 (IURC order); load in MW is redacted in the order; DCD reports local filings suggested a 12 building campus on more than 700 acres. | yes | Whether IDEM has decided isolated wetland permit SRIP01408 for Phase 3; construction start and contractors for the three Phase 3 buildings; how many of the 140 added generators are installed and how EPA will answer the petition | Check IDEM Office of Water Quality notices for a decision on isolated wetland permit SRIP01408, the City of Fort Wayne and Allen County records for Phase 3 building permits, and the EPA Title V petition database for an order on the Hatchworks petition.
Monitor | New equipment quantified in a government record; large stated scale (A planned 1,200 MW on site substation (reported by DCD)); decision Oct 7, 2026; buying window: early packages may be bought (construction is reported under way; later phases unknown) | Early packages may be bought | 2 | 1 | Pass | IN002 | Google Monrovia data center (Woodland Caribou LLC air permit at 1598 W SR 42) | Morgan | Under construction | WRTV reported on Dec 4, 2025 that initial construction started in November on Google's site between Keller Hill Road and State Road 42, the site matched by location to the Woodland Caribou LLC air permit; the IURC approved the AES Indiana Monrovia Project on Oct 7, 2026, and the IDEM air permit is still awaiting a decision after comment closed Sep 14, 2026. | https://www.wrtv.com/news/local-news/morgan-county/construction-intensifies-on-googles-morgan-county-data-center-site https://www.in.gov/iurc/files/ord_46394_100726.pdf https://www.in.gov/idem/files/notice_20260914_air_50085phext-cm.pdf | backup generators; fuel storage; cooling; water or wastewater; substation or high voltage; transmission lines; UPS or batteries | Draft air permit: 132 diesel emergency generators at 4,043 bhp (3,015 kW) and 34 at 3,569 bhp (about 2,661 kW), 3 wastewater treatment plant generators at 3,015 kW, plus smaller boost, fire pump, lift station and site generators; 179 diesel tanks up to 5,373 gallons; 36 cooling towers at 6,000 gpm. IURC order: new Antioch switchyard with a STATCOM, new Blue Bluff switchyard, double circuit 345 kV lines, 200 MW Foundry Works battery, 130 MW Hardy Hills battery, 130 MW Crosstrack solar with a 130 MW battery. The batteries and solar are utility resources, not on the data center site. |  |  |  | Oct 7, 2026 | IURC order in Cause 46394 approving the Monrovia Project and the service agreements for the Alphabet subsidiary | https://www.in.gov/iurc/files/ord_46394_100726.pdf | Woodland Caribou LLC (air permit applicant); Google (reported end user, reported by news); Alphabet Inc. subsidiary (customer named in the IURC order); AES Indiana (utility and petitioner); Indiana Utility Regulatory Commission (decision body); Indiana Department of Environmental Management (air permit decision body); Invenergy (developer of Foundry Works and Crosstrack, reported by New Project Media); Citizens Action Coalition of Indiana and AES Indiana Industrial Group (intervenors); Charles River Associates and Concentric Energy Advisors (consultants for AES Indiana) | https://permits.air.idem.in.gov/50085d.pdf https://www.in.gov/iurc/files/ord_46394_100726.pdf https://newprojectmedia.com/?p=20377 https://datacenterdynamics.com/en/news/iurc-approves-aes-indiana-plan-for-13bn-solar-storage-and-transmission-project-for-google-data-center-in-monrovia | Omar El Rjoob, IDEM Office of Air Quality permit reviewer and comment contact, Woodland Caribou draft permit; Patrick Maguire, Vice President Commercial, AES Indiana, named in the AES Indiana filing summarized in IURC order 46394 | Utility side only: the IURC order says the battery and solar resources were chosen through an all source RFP and that AES Indiana uses an engineering, procurement and construction agreement (contractor not named); New Project Media reports Invenergy develops Foundry Works and Crosstrack and that Hardy Hills is a self build. No data center contractor, generator order or bid found. | https://www.in.gov/iurc/files/ord_46394_100726.pdf https://newprojectmedia.com/?p=20377 | IURC order: Monrovia Project cost estimate 737.3 million dollars; portfolio covers 390 MW of new load with 460 MW of new 4 hour storage by 2030. DCD reports a planned 1,200 MW on site substation and a 10 mile 345 kV line. | no | Data center general and electrical contractors; when IDEM will decide the air permit; whether generators or switchgear have been ordered | Check the IDEM permit site for the Woodland Caribou final permit and its comment response, and watch IURC Cause 46394 for the updated project cost filings the order requires.
How priorities are set (the same rules for every project):
Equipment points: 2 when a government record quantifies new equipment (counts, ratings or capacity of equipment, not building area or power demand); 1 when equipment is named but not quantified, or quantified but possibly already installed; 0 when none is stated.
Scale point: 1 when a source tied to the project states at least 100 MW, $1 billion or 1 million sq ft.
Timing test: a dated public step (hearing, comment deadline, vote, planned energization) within 120 days after the status date, or a decision within the 120 days before it.
Buying window: Open or upcoming when the project is in permitting or approval with no report of equipment secured; Early packages may be bought when construction is reported under way; Main equipment may be bought when a source reports equipment or construction contracts secured; Unclear, Too early or Closed otherwise. This is a reading of public evidence, not knowledge of anyone's purchasing.
Investigate now: passes the timing test, has at least 2 points, has an Open or upcoming buying window, and faces no pending legal challenge.
Monitor: alive but misses one of those tests. Deprioritize: denied or withdrawn, the record covers only equipment already installed, or no source shows progress or a next step.
Priority says where to spend research time first. It is not a prediction that a project will be built or that anyone will buy equipment.

## Projects
ID | Project | Applicant or operator | County | City | Stage | Record type | Record date | Record | Record link | Size | Equipment stated in records | Equipment source | Milestones | Risks | Risk source | First news date | First news link | News vs record | News match (high, medium, low) | Other records | Checked on | Notes
IN005 | Lavender Fields Holdings data center expansion, 402 Royal Road (Google Michigan City) | Lavender Fields Holdings, LLC | LaPorte | Michigan City | Draft air permit modification to add critical generators to a permitted data center; under public comment through Nov 23, 2026 | Air permit | Sep 25, 2026 | IDEM public notice, Significant Source Modification 091-50515-00195 and Significant Permit Modification 091-50636-00195, Lavender Fields Holdings, LLC | https://www.in.gov/idem/files/notice_20261025_air_50515-50636pn-cm.pdf |  | Adds 67 diesel fired critical emergency generators and 67 belly tanks and removes 2 existing generators and belly tanks (notice); draft lists 66 existing generators at 2,750 kWe, 66 new critical generators GEN67 to GEN132 at 3,490 kWe (4,680 bhp) and one ancillary generator HUB1 at 167.6 bhp, HVO secondary fuel, closed loop air cooling system | https://permits.air.idem.in.gov/50515d.pdf | Jun 29, 2026 modification application received (printed in draft); Sep 25, 2026 IDEM notice posted; Nov 17, 2026 IDEM virtual public hearing; Nov 23, 2026 extended comment period end |  |  | Mar 23, 2026 | https://abc57.com/news/idem-approves-air-permit-request-for-michigan-city-data-center | News came first | high | https://permits.air.idem.in.gov/50515d.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions | Oct 20, 2026 | Same address and LLC as the initial data center permit T091-49561-00195 (noticed 2025, approved before the window; https://www.in.gov/idem/files/notice_20251213_air_49561pn-cm.pdf). This row covers the new 2026 modification. Google confirmed ownership of the site in April 2026 per DCD Apr 20, 2026; no record names Google. The notice says 67 critical generators, while the draft lists 66 critical generators (GEN67 to GEN132) plus one ancillary generator HUB1 at 167.6 bhp and 67 belly tanks; HUB1 may account for the notice's count of 67, but no document says so. The notice also says 2 existing generators and their belly tanks are removed. Earlier 2025 news exists (Inside Indiana Business) but could not be opened.
IN003 | Amazon Data Services data center campus, 2938-2778 County Rd 1350 N, Wheatfield | Amazon Data Services, Inc. | Jasper | Wheatfield | Draft Part 70 air permit for a new data center under public comment through Nov 16, 2026; county tax abatement items for Amazon Data Services heard May 19, 2026 and Jun 16, 2026 | Air permit | Sep 24, 2026 | IDEM public notice, draft Part 70 Operating Permit T 073-50413-00077, Amazon Data Services, Inc. | https://www.in.gov/idem/files/notice_20261024_air_50413pn-cm.pdf | County agenda May 19, 2026: hearing on a 330 acre Economic Revitalization Area listed with the Amazon Data Services abatement; the agenda does not say data center | 384 diesel critical emergency generators CEG1 to CEG384 at 2,750 kWe (4,043 bhp) each with SCR and cDPF (Section A.2; Section D.1 numbers their control systems CE1 to CE234); 1 ancillary 1,600 kWe generator; 4 house generators at 750 kWe; 384 belly tanks of 6,500 gallons and 14 bulk tanks of 12,000 gallons | https://permits.air.idem.in.gov/50413d.pdf | May 19, 2026 County Council hearing on 330 acre ERA with Amazon Data Services real property abatement and enterprise information technology exemption agreement; Jun 16, 2026 County Council agenda again lists Amazon abatement and exemption agreement resolutions; Sep 24, 2026 IDEM draft permit notice posted; Nov 10, 2026 IDEM virtual public hearing; Nov 16, 2026 extended comment period end |  |  | Jun 3, 2026 | https://www.datacenterdynamics.com/en/news/amazon-plans-nine-building-data-center-campus-in-wheatfield-indiana/ | News came first | high | https://permits.air.idem.in.gov/50413d.pdf https://www.in.gov/idem/files/notice_20261116_air_50413ph-cm.pdf https://www.in.gov/idem/public-notices/public-notices-all-regions https://jaspercountyin.gov/meetings/meeting-documents/county-council/2026-county-council-meetings/2026-county-council-meetings-agendas/602-05-19-2026-county-council-agenda/file https://www.jaspercountyin.gov/meetings/meeting-documents/county-council/2026-county-council-meetings/2026-county-council-meetings-agendas/622-06-16-2026-county-council-agenda/file | Oct 19, 2026 | Primary record is the IDEM notice because it is the first window record that ties Amazon Data Services to a data center at the Wheatfield address. The earlier Jasper County Council agendas (May 19, 2026 and Jun 16, 2026) name Amazon Data Services abatements and a 330 acre ERA but never say data center or give a location, so they are listed as other records matched by applicant name and county only. On the agendas alone the county record would precede the first news found (Jun 3, 2026), but that is not used because the agenda does not tie to a data center. The agendas also list a 78 acre ERA and abatement for NIPSCO investments; what those investments are is not stated in the record. The Jasper County Plan Commission listing page does not show individual agendas, so the May 18, 2026 agenda could not be confirmed directly; the check made during research found no Amazon or data center item.
IN004 | Amazon Data Services New Carlisle campus generator modification, 31100 State Road Highway 2 | Amazon Data Services, Inc | St. Joseph | New Carlisle | Draft significant permit modification to add two generators to an operating data center; comment period likely closed (end date from file name), decision pending | Air permit | Aug 17, 2026 | IDEM public notice, Significant Permit Modification 141-50312-00650, Amazon Data Services, Inc | https://www.in.gov/idem/files/notice_20260916_air_50312pn-as.pdf |  | Two new diesel ancillary emergency generators AWB1 and AWB2 at 1,600 kWe (2,360 bhp) each; with them the draft lists 5 ancillary emergency generators in total (AWB1, AWB2, CABGen1 and CLBGen1 at 400 kWe, ACBGen1 at 250 kWe), 234 critical emergency generators CEG1 to CEG234 at 2,750 kWe and 9 house generators HG1 to HG9 at 750 kWe | https://permits.air.idem.in.gov/50312d.pdf | Apr 20, 2026 application received by IDEM (printed in draft); Aug 17, 2026 comment period start (derived); Sep 16, 2026 comment period end (file name date) | enforcement notice: IDEM notice of violation dated Jun 8, 2026 for two 1,600 kW generators installed where permits allowed 1,500 kW (reported by WVPE; the letter itself was not opened) | https://www.wvpe.org/wvpe-news/2026-06-16/amazon-data-center-violates-air-permits-in-multiple-ways | Apr 25, 2024 | https://www.click2houston.com/tech/2024/04/25/amazon-cloud-computing-unit-plans-to-invest-11-billion-to-build-data-center-in-northern-indiana/ | News came first | high | https://permits.air.idem.in.gov/50312d.pdf | Oct 19, 2026 | Existing campus first permitted before the window (Part 70 permit issued May 1, 2025); this row covers the new 2026 modification record. The modification appears to permit the two 1,600 kW units named in the notice of violation, but that link is an inference. A South Bend Tribune story republished on AOL, with no printed date and probably from about April 2024, may be earlier than the first news listed (https://www.aol.com/document-sheds-light-possible-11-215126281.html); either way the news came first.
IN001 | Orla LLC data center, 3062 West SR 32, Lebanon | Orla, LLC | Boone | Lebanon | Final New Source Construction and Part 70 Operating Permit issued Sep 25, 2026 for a new stationary data center (https://permits.air.idem.in.gov/50034f.pdf) | Air permit | Jul 11, 2026 | IDEM notice of 30 day period for public comment, draft New Source Construction and Part 70 Operating Permit T 011-50034-00093, Orla, LLC | https://www.in.gov/idem/files/notice_20260810_air_50034pn-js.pdf |  | Twelve diesel fired emergency generators EG-1 through EG-12, each 4,376 bhp (Caterpillar option) or 4,352 bhp (Cummins option), HVO as secondary fuel; two 224 bhp diesel fire pumps; twelve 7,185 gallon belly tanks; Life Cycle Power permit (a separate permittee that IDEM treats as one source with the data center): 65 natural gas fired Caterpillar G3516H engine generators GEN1 to GEN65 at 2,763 hp each with SCR and oxidation catalysts, and 2 regasification boilers at 5.4 MMBtu/hr (https://permits.air.idem.in.gov/50087f.pdf) | https://permits.air.idem.in.gov/50034d.pdf | Jul 11, 2026 comment period start (derived); Aug 6, 2026 IDEM virtual public hearing; Aug 10, 2026 public comment period ends; Sep 25, 2026 IDEM issued the final permit (https://permits.air.idem.in.gov/50034f.pdf); Sep 25, 2026 IDEM issued the final Life Cycle Power permit (https://permits.air.idem.in.gov/50087f.pdf) |  |  | Nov 25, 2024 | https://wishtv.com/?p=1294631 | News came first | high | https://www.in.gov/idem/files/notice_20260810_air_50034ph-js.pdf https://permits.air.idem.in.gov/50034d.pdf https://permits.air.idem.in.gov/50034f.pdf https://www.in.gov/idem/files/notice_20260810_air_50087pn-js.pdf https://permits.air.idem.in.gov/50087f.pdf | Oct 20, 2026 | News match by applicant: WISH reported a Meta data center site on the north side of State Road 32 near Lebanon in the LEAP district, and IBJ reported on Aug 15, 2025 that the Lebanon development plan was submitted by a Meta subsidiary called Orla LLC (https://www.ibj.com/articles/lebanon-commission-to-review-metas-15-building-data-center-project). No government record names Meta. Twelve diesel generators is small for the reported Meta campus. The final permits show IDEM treats Orla, LLC and Life Cycle Power, a new gas engine power generating facility at 3602 West SR 32 (permit 50087, same comment end date), as one source because they share a property, have common control and have a support facility relationship (https://permits.air.idem.in.gov/50034f.pdf); Life Cycle Power was earlier listed as a lead and is now part of this row. The final permit URLs 50034f.pdf and 50087f.pdf were located from IDEM's file naming, then opened and confirmed as the right documents.
IN007 | NIPSCO special contract and GenCo supply for Amazon data centers in northern Indiana | Northern Indiana Public Service Company LLC and NIPSCO Generation LLC for Amazon Data Services, Inc. | Statewide or unnamed |  | IURC order on settled special contract, PPA and alternative regulatory plans; load ramps to 2,400 MW by end of 2032 | Utility docket | Jun 17, 2026 | IURC Order, Cause No. 46322, NIPSCO and NIPSCO GenCo special contract with Amazon and power purchase agreement | https://www.in.gov/iurc/files/ord_46322_061726.pdf | 2400 MW; About 7 billion dollars generation and transmission investment (NIPSCO testimony as summarized in order) | GenCo to build up to 3,000 MW for the Amazon contract: two 1,300 MW combined cycle gas plants at the Schahfer Generating Station in Jasper County, converted from two pairs of combustion turbines (2,600 MW in total), and a 400 MW battery storage system at the former Mitchell Generating Station in Lake County (IURC order 46362); 600 MW capacity confirmation with an existing thermal generator for planning year 2027 to 2028 (https://www.in.gov/iurc/files/ord_46322_061726.pdf) | https://www.in.gov/iurc/files/ord_46362_061726.pdf | Nov 7, 2025 petition filed; Jun 17, 2026 IURC order (file name date); Jun 17, 2026 IURC order in Cause 46362 declining to exercise jurisdiction over the GenCo generation resources (file name date) (https://www.in.gov/iurc/files/ord_46362_061726.pdf); Jan 1, 2027 planned start of energization under the contract | organized opposition: Citizens Action Coalition opposed the settlement in the IURC record, order dated Jun 17, 2026 | https://www.in.gov/iurc/files/ord_46322_061726.pdf | Nov 25, 2025 | https://www.utilitydive.com/news/nisource-nipsco-amazon-data-centers-indiana/806396/ | News came first | high | https://www.in.gov/iurc/files/ord_46362_061726.pdf | Oct 20, 2026 | County is Statewide or unnamed because the contract covers Amazon data centers in the NIPSCO service territory and keeps one site confidential; the order names no county or city. Possible overlap with IN003: the order cites Schahfer, and news places the Wheatfield site about half a mile from Schahfer, and IURC order 46362 places the two combined cycle plants at Schahfer in Jasper County (https://www.in.gov/iurc/files/ord_46362_061726.pdf), but neither order names Wheatfield or the Amazon site, so the rows are kept separate and may double count one campus. The text read was truncated before the final ordering paragraphs, so the final disposition was not read in the order; ScanX reported on Jun 23, 2026 that the IURC approved the settlement, special contract and power purchase agreement on June 17 (https://scanx.trade/stock-market-news/companies/nisource-secures-approval-for-amazon-data-center-deal/43764481).
IN006 | Google Fort Wayne data center (Hatchworks LLC), 7510 Zodiac Way | Google LLC through a special purpose entity (IURC); air permittee Hatchworks, LLC | Allen | Fort Wayne | Operating campus; IURC approved the I&M contract, clean capacity arrangement and demand response offering; air permit for added generators reissued Jun 1, 2026 and now under a petition to EPA; Phase 3 expansion with three more buildings received IDEM Section 401 water quality certification WQC001454 on Jun 5, 2026 (https://www.hecweb.org/wp-content/uploads/2026/06/WQC001454-Section-401-WQC-Approval.pdf); isolated wetland permit SRIP01408 for Phase 3 was heard Aug 25, 2026 and no decision was found (https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf) | Utility docket | Apr 29, 2026 | IURC Order, Cause No. 46276, Indiana Michigan Power Company customer specific contract with Google | https://secure.in.gov/iurc/files/ord_46276_042926.pdf | Initial investment 2 billion dollars announced April 2024 (IURC order); Phase 3 adds three buildings, utility infrastructure, internal drives and stormwater facilities on an 858 acre parcel (https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf) | 174 diesel emergency generators about 525 MW combined (140 added in the 2026 permit), 179 diesel tanks about 1,074,000 gallons, 64 cooling towers about 384,000 gpm. These figures are as stated in the residents' petition filed with EPA, not in the IDEM permit, which was not opened | https://www.epa.gov/system/files/documents/2026-08/hatchworks-petition_7-24-26.pdf | Apr 10, 2026 IDEM issued Part 70 permit modification 003-48840-00530 (before window, per petition); Apr 29, 2026 IURC order in Cause 46276 (file name date); Jun 1, 2026 IDEM reissued the permit (per petition); Jul 24, 2026 residents petitioned EPA to object to the permit; Jun 5, 2026 IDEM issued Section 401 water quality certification WQC001454 for Project Zodiac Phase 3 (https://www.hecweb.org/wp-content/uploads/2026/06/WQC001454-Section-401-WQC-Approval.pdf); Aug 4, 2026 IDEM published the isolated wetland permit notice SRIP01408 for Phase 3 (https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf); Aug 25, 2026 IDEM virtual public hearing on SRIP01408 (https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf); Aug 28, 2026 SRIP01408 comment period closed (https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf) | permit challenge: petition to the EPA Administrator under Clean Air Act 505(b)(2) to object to the Title V permit, filed Jul 24, 2026 | https://www.epa.gov/system/files/documents/2026-08/hatchworks-petition_7-24-26.pdf | Dec 1, 2023 | https://www.21alivenews.com/2023/12/01/allen-county-commissioners-approve-project-zodiac-annexation | News came first | medium | https://www.epa.gov/system/files/documents/2026-08/hatchworks-petition_7-24-26.pdf https://www.hecweb.org/wp-content/uploads/2026/06/WQC001454-Section-401-WQC-Approval.pdf https://www.in.gov/idem/files/notice_20260828_iwip_srip01408.pdf | Oct 20, 2026 | News match by site: 21 Alive reported Allen County approval of the Project Zodiac data center annexation on the southeast side near East Paulding Road; the permit address is 7510 Zodiac Way, but the story names no company or LLC. Inside Indiana Business (Dec 22, 2023, https://www.insideindianabusiness.com/articles/incentives-approved-for-fort-wayne-data-center-project) names Hatchworks LLC for the Fort Wayne southeast side site, which matches the EPA petition permittee (high confidence for that later story). The IURC order says Fort Wayne but not the street address; MW load is redacted. A guessed IDEM final permit URL (permits.air.idem.in.gov/48840f.pdf) failed to load and was not used. The water quality certification was read from a copy posted by the Hoosier Environmental Council; it is an IDEM Office of Water Quality document signed by Branch Chief Amari Farren for Hatchworks LLC, with EMH&T as agent. The wetland notice names the same applicant and agent and the same 858 acre parcel.
IN002 | Google Monrovia data center (Woodland Caribou LLC air permit at 1598 W SR 42) | AES Indiana for a subsidiary of Alphabet Inc. (utility docket); Woodland Caribou LLC (air permit) | Morgan | Monrovia area (air permit mailing address Mooresville) | IURC approved the AES Indiana service agreements and Monrovia Project; IDEM draft air permit 109-50085-00094 public hearing scheduled for Sep 9, 2026, comment closed Sep 14, 2026, decision pending | Utility docket | Apr 22, 2026 | IURC Order, Cause No. 46394 (petition filed Apr 22, 2026; order dated Oct 7, 2026 per its file name), AES Indiana Monrovia Project to serve a planned data center | https://www.in.gov/iurc/files/ord_46394_100726.pdf | IURC order: Monrovia Project cost estimate 737.3 million dollars, which includes the solar and battery resources as well as transmission | Air permit draft: 132 diesel emergency generators at 4,043 Bhp (3,015 kW) and 34 at 3,569 Bhp (2,661 kW), plus 3 wastewater treatment generators at 3,015 kW, HVO secondary fuel; 179 diesel tanks of 5,373 gallons; 36 cooling towers at 6,000 gpm. IURC order: new Antioch and Blue Bluff switchyards, double circuit 345 kV lines, 460 MW of battery storage and 130 MW solar | https://permits.air.idem.in.gov/50085d.pdf | Apr 22, 2026 AES Indiana petition filed in IURC Cause 46394; Jul 16, 2026 IDEM notice posted for draft permit 109-50085-00094; Jul 30, 2026 IDEM hearing scheduled then cancelled; Sep 9, 2026 rescheduled IDEM virtual public hearing; Sep 14, 2026 extended comment period end; Oct 7, 2026 IURC order (date from file name) |  |  | Feb 3, 2025 | https://www.ibj.com/articles/data-center-could-be-coming-to-morgan-county | News came first | medium | https://permits.air.idem.in.gov/50085d.pdf https://www.in.gov/idem/files/notice_2026_no_end_date_air_50085pn-cm.pdf https://www.in.gov/idem/files/notice_20260803_air_50085ph-cm.pdf | Oct 19, 2026 | Records merged by location (match by address): IDEM address 1598 W SR 42 lies on Indiana 42, the south boundary of the 391 acre Morgan Township site east of Monrovia described by IBJ; the IURC order describes a Monrovia data center for an Alphabet subsidiary served through a new Antioch switchyard, and the site is bounded by North Antioch Road. No record ties Woodland Caribou LLC to Google. The IURC order lists Morgan among AES service counties but does not name the county for the site; county rests on the IDEM record. The IURC order was located from the cause number and the vote date reported in news, then opened and confirmed; its approved date line is blank. If the IDEM permit alone were primary, the record date would be Jul 16, 2026 (posting date printed in 50085d.pdf); news is first either way.

## Leads
Project | County | What was reported | News url | Gov url seen | Why not included
Sabey Data Centers campus, 6400 Kentucky Ave, Decatur Township | Marion | 130 acre rezoning approved by MDC Mar 18, 2026 (before window); about 188 million dollars in tax abatements; MDC expected to take up incentives Sep 16, 2026; residents filed judicial review in spring 2026 | https://mirrorindy.org/indianapolis-sabey-data-centers-tax-abatement-aquatic-center-indy-economic-development/ | https://indianapolis-in.municodemeetings.com/sites/indianapolis-in.municodemeetings.com/files/fileattachments/mdc_hearing_examiner/meeting/5457/presentation_print_out_1.pdf | No project specific government record in the window was opened. The MDC meeting index blocks automated reading and meeting pages show attachment labels without links; the Jul 1, 2026 MDC presentation names Sabey only in passing.
DC Blox campus, Thunderbird Commerce Center, 305 Fintail Drive, Warren Township | Marion | Variance 2026-CVR-815 and plat 2026-CPL-815 heard by MDC Hearing Examiner May 14, 2026; recommended Jun 11, 2026; MDC approved scaled back two building plan 6 to 1 on Jul 15, 2026; originally up to 56 backup diesel generators and up to 78 MW | https://indianapublicradio.org/news/2026/07/east-side-data-center-wins-approval-despite-community-opposition/ |  | No government record was opened. The only copy of the legal notice found is hosted on the developer site (https://www.dcblox.com/wp-content/uploads/2026/04/2026CMP815-Legal-Notice.pdf), which is not a government page. MDC hearing results for Jul 15, 2026 could not be located because the municodemeetings index blocks automated reading.
Metrobloks data center, 2505 N. Sherman Ave, Martindale Brightwood | Marion | City County Council approved rezoning May 4, 2026 over organized neighborhood opposition; nearly 14 acres; exempt from the Marion County moratorium adopted Aug 19, 2026 | https://mirrorindy.org/indianapolis-council-approves-data-center-for-martindale-brightwood/ |  | No council or MDC record for the May 4, 2026 action was found or opened.
Microsoft second La Porte campus, about 1,000 acres east of Boyd Boulevard | LaPorte | La Porte Common Council approved annexation and light industrial rezoning on May 18, 2026 for 11 more data center buildings next to six under construction | https://www.wndu.com/2026/05/19/laporte-common-council-votes-favor-second-microsoft-data-center-campus/ | https://www.cityoflaporte.com/uploads/minutes/m_1937_Council-May.18-2026-Minutes.docx | The city meetings listing is readable, but minutes and agendas are posted only as .docx files, which could not be read automatically, so the vote could not be confirmed from the record.
Jefferson Proving Ground hyperscale data center campus near Madison | Jefferson | 549 acres, nine buildings, about 7.1 million square feet; Board of Zoning Appeals upheld the zoning administrator on May 20, 2026 that no special exception was needed; plan commission declined to start a moratorium Sep 1, 2026; Duke Energy Indiana territory | https://climate.uchicago.edu/?p=18878 | https://www.jeffersoncounty.in.gov/AgendaCenter/ViewFile/Minutes/_05202026-827 | The May 20, 2026 BZA minutes PDF has no machine readable text (scanned) and the BZA agenda and other AgendaCenter files blocked automated reading, so the action could not be confirmed from a record.
Qlever LLC and ION Louis LLC data center, Shadow Lake Business Park, Charlestown | Clark | Charlestown Advisory Plan Commission voted 4 to 3 on a Monday (likely Jul 20, 2026) to advance a roughly 55,000 square foot data center of up to 5 MW with stipulations (berm, blasting surveys, environmental study); also spelled QLEVR in other reports | https://www.lpm.org/news/2026-07-21/charlestown-board-advances-data-center-proposal-with-stipulations |  | No Charlestown government record was found: searches for city plan commission agendas or minutes returned only other towns named Charlestown, and a News and Tribune story about the vote did not load.
Vermillion Rise Mega Park data center project | Vermillion | On Aug 25, 2026 commissioners scrapped an earlier ordinance governing a data center project and formed a committee to draft new rules after about three hours of public comment; a one year moratorium was raised | https://www.bondbuyer.com/news/indiana-counties-response-to-data-centers-reflects-broader-political-risk |  | No county record found or opened; developer not named.

## Sources
Family | Source | Link | Access | Notes
1. State air permit public notices | IDEM public notices, all regions listing | https://www.in.gov/idem/public-notices/public-notices-all-regions | Read | Lists only notices currently open (seen range Sep 1, 2026 to Nov 23, 2026). Notices from April to August 2026 have dropped off; they were found by site searches of in.gov for each month of the window.
1. State air permit public notices | IDEM public notice PDFs (in.gov/idem/files) | https://www.in.gov/idem/files/ | Read | Notice text usually omits the posting date; file names carry the comment end date.
1. State air permit public notices | IDEM Office of Air Quality draft permits (permits.air.idem.in.gov) | https://permits.air.idem.in.gov/ | Read | Draft permits at <permit number>d.pdf give full generator lists and often print the notice posting date; used for equipment evidence and record dates. One guessed final permit URL (48840f.pdf) failed to load.
1. State air permit public notices | IDEM Online Air Permit Search (CAATS) and Virtual File Cabinet | http://www.in.gov/ai/appfiles/idem-caats | Not checked in this scan | Search applications; not used. Final permit issuance dates and notices of violation sit here.
1. State air permit public notices | IDEM fact sheet, IDEM and data centers | https://www.in.gov/idem/files/factsheet_idem_and_datacenters.pdf | Read | General guidance; no project list.
2. State regional impact or large project review | None in Indiana |  | Not used in this state | Indiana has no statewide regional impact or large project review program.
3. Utility commission dockets | IURC order files (in.gov/iurc/files) | https://www.in.gov/iurc/files/ | Read | Orders found by search and by the commission's file naming (cause number and order date), each opened and confirmed. The approved date line was blank in the text read for each order.
3. Utility commission dockets | IURC electronic docket system |  | Not checked in this scan | Not searched, so pending large load petitions without an order were not checked.
4. County and city planning | Indianapolis MDC and Hearing Examiner (municodemeetings) | https://indianapolis-in.municodemeetings.com/ | Blocks automated reading | The site blocks automated reading from its main pages. Some meeting pages and PDFs were readable when found by search, but meeting pages show attachment labels without links.
4. County and city planning | Jefferson County IN AgendaCenter | https://www.jeffersoncounty.in.gov/AgendaCenter | Blocks automated reading | Listing page readable; most documents block automated reading; one minutes file was a scanned PDF with no text.
4. County and city planning | City of La Porte meetings | https://www.cityoflaporte.com/meetings/ | Read | Listing readable; agendas and minutes are posted as Word files, which could not be read.
4. County and city planning | Jasper County Plan Commission agendas | https://jaspercountyin.gov/agenda-library/planning-and-development/plan-commission/ | Read | The Jasper County Plan Commission listing page does not show individual agendas, so the May 18, 2026 agenda could not be confirmed directly; the check made during research found no Amazon or data center item.
4. County and city planning | Morgan County planning |  | Not checked in this scan | Not checked; IDEM and IURC records used instead.
4. County and city planning | Boone County and City of Lebanon planning |  | Not checked in this scan | Not checked; IDEM records used instead.
4. County and city planning | St. Joseph County planning |  | Not checked in this scan | Not checked; IDEM records used instead.
4. County and city planning | City of Charlestown planning |  | Not checked in this scan | Official site not found by search; results returned other towns named Charlestown.
5. State and local incentive approvals | Jasper County Council agendas | https://www.jaspercountyin.gov/meetings/meeting-documents/county-council/ | Read | May 19, 2026 and Jun 16, 2026 agendas list Amazon Data Services abatement resolutions; they do not say data center.
5. State and local incentive approvals | Indiana Economic Development Corporation | https://www.iedc.in.gov/ | Not checked in this scan | Not searched for new records; its Feb 11, 2026 release on the Meta Lebanon campus is cited for IN001.
0. News leads | Web search news (WFYI, IPR, Mirror Indy, IBJ, DCD, WNDU, ABC57, LPM, Bond Buyer) |  | Read | Used for leads and news comparison only.
0. News leads | Inside Indiana Business | https://www.insideindianabusiness.com/ | Did not load | Most article pages could not be read; one older article (Dec 22, 2023) did load.

## Coverage gaps
Indiana (IN) coverage gaps, window Apr 18, 2026 to Oct 18, 2026
State air permit public notices (IDEM)
Readable. The IDEM all regions listing only shows notices that are open now (seen range Sep 1, 2026 to Nov 23, 2026). Notices posted from April to August 2026 are no longer listed. The in.gov domain was site searched for data center air notices for each month of the window (April through October 2026); no notices beyond those already in the scan turned up. Some notices may still be missed because only search engine indexed files can be found this way. Notice text usually does not print the posting date. Where the draft permit package prints it (IN002, IN003, IN005) that date is used; otherwise the date is derived as the deadline minus the stated 30 days (IN001), or as the file name date minus 30 days (IN004). Final permit issuance dates and notices of violation sit in the IDEM Virtual File Cabinet and the CAATS search, which were not checked. Effect: medium. Air permits are the strongest family here, but spring and summer 2026 coverage is incomplete.
State regional impact or large project review
Not applicable. Indiana has no statewide regional impact review program. No effect.
Utility commission dockets (IURC)
Readable for order PDFs. Four data center orders in the window were found and opened (Causes 46276, 46322, 46362, 46394). Cause 46362 is the order on the NIPSCO GenCo plants tied to the Amazon contract; in it the Commission declined to exercise jurisdiction. The IURC electronic docket system was not checked, so pending large load petitions without an order (for example Duke Energy Indiana or Indiana Michigan Power filings for other sites) were missed. Each order read had a blank approved date line, so order dates come from file names. The 46322 text was truncated before the final ordering paragraphs. Effect: medium.
County and city planning
Partly blocked.
Indianapolis (Marion County): the municodemeetings site root blocks automated reading, and meeting pages show attachment labels without links. Three projects with approvals in the window (Sabey, DC Blox, Metrobloks) are in leads only. Effect: high for Marion County.
Jefferson County: most AgendaCenter files block automated reading, and the May 20, 2026 BZA minutes are a scanned PDF with no text. The Jefferson Proving Ground campus is in leads only.
City of La Porte: the meetings listing is readable, but minutes and agendas are .docx files that could not be read automatically. The Microsoft second campus is in leads only.
City of Charlestown (Clark County): no official meeting records were found by search. The Qlever data center is in leads only.
Jasper County Plan Commission: The Jasper County Plan Commission listing page does not show individual agendas, so the May 18, 2026 agenda could not be confirmed directly; the check made during research found no Amazon or data center item.
Boone, Morgan, St. Joseph, Allen and LaPorte county planning sites were not checked for window items.
Effect: high. Local land use approvals are undercounted.
State and local incentive approvals
Jasper County Council agendas are readable, but they name Amazon Data Services without saying data center. IEDC and other county councils were not checked. Effect: medium.
Local moratoriums
These moratoriums and bans are not tied to one project, so they are not project rows. Links marked "opened" were read in this run; the others were seen only in search results and were not opened.
Marion County (Indianapolis): MDC adopted a pause on new data centers on Aug 19, 2026; Sabey, DC Blox and Metrobloks are exempt as previously approved. Opened: https://www.wfyi.org/wfyi-news/2026-08-19/new-data-centers-temporarily-banned-in-marion-county
Boone County: one year data center moratorium, June 2026. Not opened: https://www.youarecurrent.com/2026/06/15/boone-county-installs-one-year-data-center-moratorium/
Switzerland County: one year moratorium passed at a special meeting on Aug 31, 2026. Opened: https://www.bondbuyer.com/news/indiana-counties-response-to-data-centers-reflects-broader-political-risk
Jefferson County: plan commission declined to begin a moratorium on Sep 1, 2026. Same Bond Buyer story, opened.
Vermillion County: a one year moratorium was raised on Aug 25, 2026. Same Bond Buyer story, opened.
Jeffersonville: year long data center moratorium, August 2026; Meta campus not affected. Not opened: https://www.wave3.com/2026/08/04/jeffersonville-passes-year-long-data-center-moratorium-amid-resident-outcry-major-utility-disclosures/
Charlestown: council one year moratorium on data centers, date not confirmed. Not opened: https://www.newsandtribune.com/news/charlestown-council-approves-one-year-moratorium-on-data-centers/article_e65aef39-4efd-4c3e-9773-593d4232bd53.html
Wabash County: ordinance 2026-85-08 imposing a temporary moratorium on data centers. Government record, not opened: https://secure.in.gov/counties/wabash/files/ordinances/2026-85-08-Ordinance-Imposing-a-Temporary-Moratorium-on-Data-Centers.pdf
Washington County: 12 month moratorium on large data centers, date not confirmed. Not opened: https://cpo.soar.com/articles/8920264/Washington-County/Indiana/Washington-County-adopts-12-month-moratorium-on-large-data-centers
Marshall County: permanent ban in April 2026. Fulton, Pulaski and Starke counties: active one year moratoriums. Opened: https://abc57.com/news/michiana-data-center-roundup
Fulton County: one year moratorium on Mar 3, 2026, before the window. Not opened: https://www.953mnc.com/2026/03/03/fulton-county-commissioners-approve-one-year-moratorium-on-new-data-center-development/
Statewide count: about 25 of 92 counties had moratoriums and 3 had bans as of September 2026, per Indiana University Environmental Resilience Institute figures cited by Bond Buyer (opened). The IU page itself (opened: https://eri.iu.edu/resources/fact-sheets/data-centers.html) gives July 2026 counts without naming counties.
News and leads
News was used for leads and for the news comparison. Inside Indiana Business article pages mostly could not be read, which may hide earlier first news dates. Earliest news dates are the earliest found, not proven earliest.